## Instructions
Site Activation Tracker
Clinical Trial Start-Up Toolkit — Component 4 of 12
How this workbook works
This tracker monitors every candidate site from contract execution through to formal activation (the “Green Light” letter referenced in the Study Start-Up Checklist, Toolkit Component 1, Phase 6). Enter each milestone date as it happens; Days to Activation and Status calculate automatically, and the Dashboard sheet gives you a live, chartable view of activation progress across every site.
Milestones tracked, in order
Contract Executed → Essential Documents Complete (Component 5) → Regulatory/EC Approval → Site Initiation Visit (SIV) Completed → Investigational Product Shipped → IP Received & Verified → EDC Access Granted → IRT Access Granted → Activation Letter Issued.
Status logic
Not Started — no contract date entered yet.
In Progress — contract executed, activation letter not yet issued, within the target window.
Delayed — contract executed more than the target number of days ago (default 49 days / 7 weeks) with no activation letter issued. Change the target in cell C5 of the Activation Tracker sheet.
Activated — activation letter issued; Days to Activation is fixed at that point.
Color legend
Blue-filled cells are for your input (dates and Yes/No fields). White cells contain formulas — do not overwrite them.
Educational and operational resource notice: this workbook is a professional starting framework based on common industry practice. It is not a substitute for your organization's own SOPs and does not constitute regulatory or legal advice. Adapt milestones and the target timeline to your protocol.

## Activation Tracker
Site Activation Tracker
Enter one row per site. Days to Activation and Status calculate automatically.
Target days to activation (contract → activation letter): |  |  |  | 49 | days (default: 7 weeks)
Site ID | Site Name | Country | Principal Investigator | Contract Executed | Essential Docs Complete | Regulatory / EC Approval | SIV Completed | IP Shipped | IP Received & Verified | EDC Access Granted | IRT Access Granted | Activation Letter Issued | Days to Activation | Status | Notes
S-01 | University Medical Center Alpha | Spain | Dr. A. Martinez | 2026-06-10 | 2026-06-20 | 2026-06-28 | 2026-07-12 | 2026-07-15 | Yes | Yes | Yes | 2026-07-27 | 47 | Activated | Example row — fully activated on schedule
Formulas:
Days to Activation = IF([Contract Executed]="","",IF([Activation Letter Issued]="",TODAY()-[Contract Executed],[Activation Letter Issued]-[Contract Executed]))
Status = IF([Site ID]="","",IF([Contract Executed]="","Not Started",IF([Activation Letter Issued]<>"","Activated",IF((TODAY()-[Contract Executed])>E4,"Delayed","In Progress"))))

## Dashboard
Activation Dashboard
Live summary — updates automatically as you enter milestone dates.
Sites Tracked | 1
Sites Activated | 1
Sites In Progress | 0
Sites Delayed | 0
Sites Not Started | 0
Average Days to Activation (activated sites) | 47
Days to Activation by Site
Site Name | Days to Activation
University Medical Center Alpha | 47