## Instructions
Start-Up Timeline
Clinical Trial Start-Up Toolkit — Component 6 of 12
How this workbook works
This is a Gantt-style planner for the same 9 phases used throughout the toolkit — the Study Start-Up Checklist (Component 1), the Risk Register (Component 7), and the RACI Matrix (Component 8) all reference the same phase numbers, so the whole toolkit stays aligned to one shared plan.
How the bars are generated
Each phase has a Start Week and an End Week (both editable, blue-filled cells), expressed relative to planned site activation (“Week 0”). The colored bar across the week grid on the right is generated automatically by conditional formatting — change the Start or End Week and the bar redraws itself. No chart object to reposition, and it copies cleanly into a slide or PDF status report.
Default timing
The default Start/End weeks match the “Typical timing” shown for each phase in the Study Start-Up Checklist (Component 1). Adjust them freely for your protocol — country mix, IRB pathway (central vs. local), and therapeutic area all affect realistic start-up duration.
Tracking actual progress
Use the % Complete column to record real progress against each phase at your weekly status meeting. The Status column flags a phase red if today's date falls after its planned End Week and % Complete is still below 100%.
Color legend
Blue-filled cells are for your input (Start Week, End Week, Owner, % Complete, Notes). White cells contain formulas — do not overwrite them. Navy bars in the week grid represent the 9 start-up phases; the coral marker on the last row represents the single-point First Patient In milestone.
Educational and operational resource notice: this timeline is a professional starting framework based on common industry practice. It is not a substitute for your organization's own SOPs and does not constitute regulatory or legal advice. Adapt phase timing to your protocol, country mix, and regulatory pathway.

## Timeline
Start-Up Timeline — Gantt View
Weeks are relative to planned site activation (Week 0). Edit Start/End Week to redraw each bar.
Planned Week 0 date (site activation): |  |  |  | 2026-10-15
# | Phase / Milestone | Start Week | End Week | Owner | % Complete | Notes | W-12 | W-11 | W-10 | W-9 | W-8 | W-7 | W-6 | W-5 | W-4 | W-3 | W-2 | W-1 | W0 | W1 | W2 | Status
1 | Phase 1 — Protocol & Feasibility Finalization | -12 | -10 | Sponsor / Clin Ops | 0% | [16 empty] | On Track
2 | Phase 2 — Regulatory & Ethics Submissions | -10 | -6 | Regulatory Affairs | 0% | [16 empty] | On Track
3 | Phase 3 — Site Identification & Selection | -12 | -8 | Feasibility Team | 0% | [16 empty] | On Track
4 | Phase 4 — Contracts & Budget | -10 | -6 | Legal / Contracts | 0% | [16 empty] | On Track
5 | Phase 5 — Essential Document Collection (TMF) | -8 | -4 | CRA / TMF Lead | 0% | [16 empty] | On Track
6 | Phase 6 — Site Activation | -6 | -2 | Project Manager | 0% | [16 empty] | On Track
7 | Phase 7 — Systems, Training & Communication | -8 | 0 | Project Manager | 0% | [16 empty] | On Track
8 | Phase 8 — Recruitment Readiness | -4 | 0 | Recruitment Lead | 0% | [16 empty] | On Track
9 | Phase 9 — Final Readiness Review | 0 | 0 | Project Manager | 0% | [16 empty] | On Track
◆ | First Patient In (FPI) | 0 | 0 | CRA / Project Manager | 0%
[7 empty] | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2
Formulas:
Status = IF(F5>=1,"Complete",IF(AND(TODAY()>(E3+[End Week]*7),F5<1),"Behind Schedule","On Track"))

## Phase Reference
Phase Reference
Same 9 phases used across the Study Start-Up Checklist, Risk Register, and RACI Matrix.
Phase | Purpose
Phase 1 — Protocol & Feasibility Finalization | Lock the scientific and operational basis of the study before any regulatory or site-facing activity begins.
Phase 2 — Regulatory & Ethics Submissions | Usually the longest pole in start-up; track every submission and query against this window.
Phase 3 — Site Identification & Selection | Runs in parallel with Phases 1–2; feeds the Site Selection Scorecard (Component 3).
Phase 4 — Contracts & Budget | No essential-document collection should begin ahead of a fully executed agreement.
Phase 5 — Essential Document Collection (TMF) | A site cannot be activated until every applicable document (Component 5) is filed.
Phase 6 — Site Activation | The formal go/no-go gate; all items must close before the activation letter is issued.
Phase 7 — Systems, Training & Communication | Runs in parallel; establishes the operating rhythm the study team uses for the life of the trial.
Phase 8 — Recruitment Readiness | Materials and screening tools must be approved and in site hands before activation.
Phase 9 — Final Readiness Review | The final gate; formal record that the team reviewed every open item before authorizing enrollment.