## Instructions
Risk Register
Clinical Trial Start-Up Toolkit — Component 7 of 12
How this workbook works
Log every risk to on-time, on-budget site activation here — regulatory, operational, vendor, financial, clinical, data/systems, or personnel. Score each risk on Likelihood and Impact (1–5); Risk Score and Risk Level calculate automatically using the same 5×5 matrix shown on the Risk Matrix sheet. Four example risks are pre-filled to show the intended level of detail — replace or extend them with your own.
Scoring the matrix
Likelihood: 1 = Rare, 2 = Unlikely, 3 = Possible, 4 = Likely, 5 = Almost Certain.
Impact: 1 = Negligible, 2 = Minor, 3 = Moderate, 4 = Major, 5 = Severe (see the Risk Matrix sheet for impact definitions specific to clinical trial start-up).
Risk Score = Likelihood × Impact (1–25). Risk Level: 1–4 Low, 5–9 Medium, 10–15 High, 16–25 Critical.
Linking risks to the rest of the toolkit
Use the Phase column to reference the same 9 phases used in the Study Start-Up Checklist (Component 1) and Start-Up Timeline (Component 6), so a delayed phase and its driving risk are easy to cross-reference in your weekly status report (Component 11).
Status workflow
Open — identified, mitigation not yet fully in place. In Progress — mitigation actions underway. Mitigated — mitigation complete; residual risk accepted or monitored. Closed — risk no longer applies. Escalated — raised to sponsor/governance for a decision beyond the project team's authority.
Color legend
Blue-filled cells are for your input. White cells contain formulas — do not overwrite them.
Educational and operational resource notice: this register is a professional starting framework based on common industry practice. It is not a substitute for your organization's own SOPs and does not constitute regulatory or legal advice. Calibrate Likelihood/Impact definitions and thresholds to your organization's risk appetite.

## Risk Register
Risk Register
Score each risk 1–5 on Likelihood and Impact. Risk Score and Risk Level calculate automatically.
Risk ID | Risk Description | Category | Phase | Likeli- hood | Impact | Risk Score | Risk Level | Mitigation Plan | Owner | Status | Date Identified | Notes
R-01 | Central IRB/EC approval takes longer than the planned 4-week window, delaying Phase 2 submissions across all countries. | Regulatory | Phase 2 | 4 | 4 | 16 | Critical | Submit to IRB/EC 1 week ahead of internal target; assign Regulatory Affairs a weekly tracking call with the IRB coordinator; identify an expedited-review pathway as a fallback. | Regulatory Affairs | Open | 2026-06-01
R-02 | Highest-enrolling site (per feasibility) experiences PI departure or staff turnover during start-up, jeopardizing enrollment commitment. | Personnel / Resourcing | Phase 6 | 2 | 5 | 10 | High | Confirm a qualified sub-investigator is named and trained at site activation; maintain the backup site identified in Component 3 as a contingency. | Project Manager | Open | 2026-06-05
R-03 | Investigational product shipment delayed at customs in a non-EU country, pushing site activation past the planned date. | Vendor / Supply Chain | Phase 6 | 3 | 4 | 12 | High | Confirm import license and customs documentation (Phase 2) at least 3 weeks before planned shipment; engage a customs broker with prior IP experience in-country. | Pharmacy / Vendor Mgmt | In Progress | 2026-06-10
R-04 | Site contract negotiation stalls over indemnification language, delaying essential document collection. | Financial / Budget | Phase 4 | 3 | 3 | 9 | Medium | Use the master Clinical Trial Agreement template's pre-approved indemnification clause; escalate to Legal if unresolved after 2 rounds of redlines. | Legal / Contracts | Mitigated | 2026-05-20

## Risk Matrix
5×5 Risk Matrix — Live Heat Map
Each cell shows the number of logged risks at that Likelihood × Impact combination.
Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 1 | 0
3 | 0 | 0 | 1 | 1 | 0
2 | 0 | 0 | 0 | 0 | 1
1 | 0 | 0 | 0 | 0 | 0
Low (1–4)
Medium (5–9)
High (10–15)
Critical (16–25)
Impact Definitions (clinical trial start-up context)
1 — Negligible |  | No effect on timeline, budget, or quality; resolved within normal operations.
2 — Minor |  | Localized delay (<1 week) or minor cost overrun; no escalation needed.
3 — Moderate |  | Phase-level delay (1–3 weeks) or budget variance requiring PM attention.
4 — Major |  | Site activation or FPI at risk of missing target by weeks; sponsor visibility required.
5 — Severe |  | Trial-level delay, regulatory non-compliance, or patient safety implication.

## Dashboard
Risk Dashboard
Live summary — updates automatically as you log and score risks.
Total Risks Logged | 4
Critical | 1
High | 2
Medium | 1
Low | 0
Open / Escalated | 2
Mitigated / Closed | 1
Risks by Category
Category | Count
Regulatory | 1
Site / Operational | 0
Vendor / Supply Chain | 1
Financial / Budget | 1
Clinical / Safety | 0
Data / Systems | 0
Personnel / Resourcing | 1