## Instructions
Vendor Onboarding Checklist
Clinical Trial Start-Up Toolkit — Component 9 of 12
How this workbook works
Clinical trials depend on multiple third-party vendors — central labs, IRT/RTSM, imaging, translation, courier/logistics, eCOA/ePRO, and safety/pharmacovigilance providers among them. This workbook has two views: a detailed 30-item Onboarding Checklist for walking a single vendor from selection to go-live, and a Multi-Vendor Tracker for a one-line-per-vendor view across every vendor on the study.
Onboarding Checklist sheet
Use one copy of this checklist per vendor (duplicate the sheet, or the whole workbook, for each). The 30 items are grouped into 4 stages: Selection & Due Diligence, Contractual & Compliance Setup, Operational & Systems Setup, and Go-Live Readiness. A vendor should not be considered ready for site activation (see the Study Start-Up Checklist, Component 1, Phase 6) until Stage 4 is complete.
Multi-Vendor Tracker sheet
Use this as your single source of truth for vendor onboarding status across the whole study — one row per vendor, with Onboarding Status calculated automatically from the dates and milestones you enter.
Cross-reference
For a formal, ongoing vendor governance model (RFPs, KPI dashboards, escalation matrices, quarterly business reviews) once vendors are onboarded, see the companion CRO Selection & Oversight Toolkit.
Color legend
Blue-filled cells are for your input. White cells contain formulas — do not overwrite them.
Educational and operational resource notice: this checklist is a professional starting framework based on common industry practice. It is not a substitute for your organization's own SOPs and does not constitute regulatory or legal advice. Adapt stages and items to your vendor type and internal procurement / quality requirements.

## Onboarding Checklist
Vendor Onboarding Checklist
One copy per vendor. Update Status, Date Completed, and Notes as onboarding progresses.
Vendor Name
Vendor Type
Contract Start Date
Onboarding Owner
# | Checklist Item | Status | Date Completed | Notes
STAGE 1 — Selection & Due Diligence
1 | Vendor identified and added to preferred vendor list / RFP issued | Not Started
2 | References checked and prior performance reviewed | Not Started
3 | Financial stability and business continuity assessment completed | Not Started
4 | Quality system and certifications reviewed (e.g., ISO, GxP compliance) | Not Started
5 | Data privacy and security assessment completed (GDPR, 21 CFR Part 11 as applicable) | Not Started
6 | Capability assessment completed against protocol-specific requirements | Not Started
7 | Bid / quote received and reviewed against budget | Not Started
8 | Vendor selection approved by Sponsor / Procurement | Not Started
STAGE 2 — Contractual & Compliance Setup
1 | Confidentiality Disclosure Agreement executed | Not Started
2 | Master Service Agreement / vendor contract executed | Not Started
3 | Quality Agreement executed, where applicable | Not Started
4 | Data Processing Agreement / GDPR addendum executed | Not Started
5 | Insurance certificate obtained | Not Started
6 | Vendor added to sponsor's approved vendor list / procurement system | Not Started
7 | Purchase order / budget line raised | Not Started
8 | Vendor oversight plan drafted (see CRO Selection & Oversight Toolkit) | Not Started
STAGE 3 — Operational & Systems Setup
1 | Kickoff meeting held with vendor project team | Not Started
2 | Roles, responsibilities, and communication plan agreed | Not Started
3 | Vendor-specific specifications finalized (e.g., lab manual, IRT spec, imaging charter) | Not Started
4 | System access provisioned for study team, if applicable | Not Started
5 | Integration with EDC / other systems tested, if applicable | Not Started
6 | Vendor staff trained on protocol and study-specific procedures | Not Started
7 | Escalation contacts and out-of-hours coverage confirmed | Not Started
8 | Vendor documentation filed in TMF (Essential Document Checklist, Component 5) | Not Started
STAGE 4 — Go-Live Readiness
1 | User acceptance testing (UAT) completed and signed off, if applicable | Not Started
2 | Vendor confirmed ready to support first site activation | Not Started
3 | Vendor KPIs and SLAs documented and agreed | Not Started
4 | First deliverable tested end-to-end (e.g., first shipment, first randomization) | Not Started
5 | Vendor oversight cadence scheduled (recurring calls, KPI reviews) | Not Started
6 | Final go-live sign-off obtained from Project Manager | Not Started
Overall % Complete: |  | 0%

## Multi-Vendor Tracker
Multi-Vendor Onboarding Tracker
One row per vendor. Onboarding Status calculates automatically.
Vendor Name | Vendor Type | Contract Executed | Kickoff Held | UAT / Systems Complete | Go-Live Ready | Owner | Onboarding Status | Notes
Synevo Central Lab | Central Lab | 2026-05-15 | Yes | Yes | Yes | Vendor Mgmt | Ready

## Dashboard
Vendor Onboarding Dashboard
Live summary from the Multi-Vendor Tracker sheet.
Vendors Tracked | 1
Ready for Go-Live | 1
In Progress | 0
Not Started | 0
Vendors by Type
Type | Count
Central Lab | 1
IRT / RTSM | 0
Imaging | 0
Translation | 0
Courier / Logistics | 0
eCOA / ePRO | 0
Safety / Pharmacovigilance | 0
CRO Functional Service | 0
Other | 0