## Instructions
Recruitment Feasibility Template
Clinical Trial Start-Up Toolkit — Component 10 of 12
How this workbook works
Patient recruitment is the single most common cause of clinical trial delay. This workbook helps you stress-test enrollment assumptions before the study starts, monitor the competitive landscape at each site, and track actual enrollment against plan once the study is live — so slippage is caught in month one, not month nine.
Site Feasibility Calculator sheet
Enter study-wide assumptions (total target enrollment, planned enrollment period) at the top, then one row per site with its target, eligible patient pool, historical screen failure rate, and realistic monthly screening rate. The sheet automatically calculates each site's expected monthly enrollment rate, the number of months it will take to reach its target, and a Feasibility Rating (Feasible / At Risk / Not Feasible) benchmarked against the planned enrollment period.
Competing Studies Log sheet
Track other trials competing for the same patient population at each site. A high volume of competing studies in the same indication is one of the strongest predictors of recruitment shortfall and should feed directly back into the Feasibility Calculator's screening-rate assumptions.
Enrollment Projection Tracker sheet
Once the study is enrolling, log actual cumulative enrollment by month against the planned curve (calculated automatically from your study-wide target and period). The variance and chart make it immediately visible whether the study is on track, and by how much.
Dashboard sheet
A live, single-page summary — feasibility distribution across sites, current enrollment vs. target, and months remaining — for status updates and steering committee reporting.
Cross-reference
Use alongside the Country and Site Feasibility Questionnaire (Component 2) and Site Selection Scorecard (Component 3) during site selection, and the Patient Recruitment & Screening Funnel tracker (companion product) once the study is enrolling for granular, per-subject funnel tracking.
Color legend
Blue-filled cells are for your input. White cells contain formulas — do not overwrite them.
Educational and operational resource notice: this template is a professional starting framework based on common industry practice for recruitment feasibility planning. It is not a substitute for statistical sample-size or power calculations, epidemiological data specific to your protocol, or your organization's own SOPs, and does not constitute regulatory or legal advice.

## Site Feasibility Calculator
Site Feasibility Calculator
Set study-wide assumptions below, then complete one row per candidate or activated site.
Study-Wide Target Enrollment (subjects) |  |  |  | 240
Planned Enrollment Period (months) |  |  |  | 12
Number of Sites Planned |  |  |  | 12
# | Site ID / Name | Country | Site Target Enrollment | Eligible Patient Pool (est.) | Historical Screen Failure Rate | Est. Monthly Screening Rate | Competing Trials at Site | Est. Monthly Enrollment Rate | Months to Site Target | Feasibility Rating | Notes
1 | Site 04 — Hospital Universitario La Fe | Spain | 24 | 180 | 35% | 14 | 2 | 9.1 | 2.6 | Feasible | Example — replace with site data
2
3
4
5
6
7
8
9
10
11
12
Sum of Site Targets: |  |  | 24
Variance vs. Study-Wide Target: |  |  | -216

## Competing Studies Log
Competing Studies Log
Log other trials competing for the same patient population at each site.
# | Site ID / Name | Competing Protocol / Study ID | Sponsor | Indication | Same Target Population? | Estimated Impact on Enrollment | Status | Notes
1 | Site 04 — Hospital Universitario La Fe | NCT-EXT-2291 | Competitor Sponsor Inc. | Same indication, earlier line of therapy | Yes | High | Recruiting | Opened 2 months before this study; same PI network
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## Enrollment Projection Tracker
Enrollment Projection Tracker
Planned Cumulative is calculated from the study-wide target and period on the Site Feasibility Calculator sheet.
# | Month | Planned Cumulative Enrollment | Actual Cumulative Enrollment | Variance | Notes
1 | Month 1 | 20 | 16 | -4 | First site activated mid-month
2 | Month 2 | 40 | 35 | -5
3 | Month 3 | 60 | 49 | -11 | Two sites still pending activation
4 | Month 4 | 80
5 | Month 5 | 100
6 | Month 6 | 120
7 | Month 7 | 140
8 | Month 8 | 160
9 | Month 9 | 180
10 | Month 10 | 200
11 | Month 11 | 220
12 | Month 12 | 240
13 | Month 13 | 240
14 | Month 14 | 240
15 | Month 15 | 240
16 | Month 16 | 240
17 | Month 17 | 240
18 | Month 18 | 240

## Dashboard
Recruitment Feasibility Dashboard
Live summary from the Site Feasibility Calculator and Enrollment Projection Tracker.
Study-Wide Target Enrollment | 240
Planned Enrollment Period (months) | 12
Sites Rated Feasible | 1
Sites Rated At Risk | 0
Sites Rated Not Feasible | 0
Current Actual Enrollment | 49
% of Target Achieved | 20.42%
Site Feasibility Distribution
Rating | Sites
Feasible | 1
At Risk | 0
Not Feasible | 0