CLINICAL TRIAL START-UP TOOLKIT Weekly Status Report Template Component 11 of 12 — Standardized Weekly Reporting Format for Sponsors & Steering Committees Sample Document — Prepared for Internal Review Includes all 12 components — single-user license, not for redistribution Version 1.0 — 3 August 2026 expertclinicaltrials.com

# About This Toolkit Component

This Weekly Status Report Template is Component 11 of the Clinical Trial Start-Up Toolkit. It gives the study team a single, consistent format for reporting start-up and enrollment progress to the sponsor, steering committee, or internal leadership on a weekly cadence — so every stakeholder sees the same picture, in the same order, every week.

The template pulls together the outputs of the other components in this toolkit into one status snapshot: activation progress from the Site Activation Tracker (Component 4), enrollment projections from the Recruitment Feasibility Template (Component 10), open items from the Risk Register (Component 7), and near-term dates from the Start-Up Timeline (Component 6). Completing it should take a study manager 20–30 minutes once the underlying trackers are up to date.

## Instructions for Use

- Complete this report on the same day each week (e.g., every Friday) so the reporting cadence is predictable for recipients.

- Pull figures directly from your Site Activation Tracker, Recruitment Feasibility Template, and Risk Register rather than re-estimating — the numbers should always reconcile.

- Set the RAG (Red/Amber/Green) status for each work stream deliberately: Green = on track, no action needed; Amber = at risk, being actively managed; Red = off track, escalation or decision required.

- Keep the Executive Summary to 3–5 bullet points. Detail belongs in the sections below, not the summary.

- Carry forward open action items and risks week over week until they are closed — do not let items silently drop off the report.

- Distribute the completed report to the standing distribution list within 24 hours of the reporting period closing.

Educational and operational resource notice:  This template is a professional starting framework based on common industry practice. It is not a substitute for your organization's own SOPs, sponsor-mandated reporting formats, or contractual reporting obligations, and does not constitute regulatory or legal advice. Adapt sections and thresholds to your study and governance structure.

# Weekly Status Report

| Question | Response |
| --- | --- |
| Protocol number / Study title |  |
| Sponsor / CRO |  |
| Reporting period (week of) |  |
| Report prepared by (name, role) |  |
| Distribution list |  |
| Overall Project Status | Green ☐ Amber ☐ Red ☐ |

## Section A: Executive Summary

3–5 bullet points capturing the most important developments this reporting period. Write for a reader who has not seen last week's report.

- Key highlight or milestone achieved this period —

- Key concern or risk requiring attention —

- Decision or input needed from sponsor / steering committee —

- Change from last week's status (what moved, and why) —

## Section B: RAG Status by Work Stream

Mark each work stream Green, Amber, or Red for both last week and this week so trend is visible at a glance.

| Work Stream | Last Week | This Week | Trend | Comments |
| --- | --- | --- | --- | --- |
| Regulatory & Ethics Approvals |  |  |  |  |
| Contracts & Budget |  |  |  |  |
| Site Activation |  |  |  |  |
| Recruitment & Enrollment |  |  |  |  |
| Vendors & Third Parties |  |  |  |  |
| IP / Supply Chain |  |  |  |  |
| Systems & Data (EDC / IRT) |  |  |  |  |

RAG definitions:

- Green — on track against plan; no action needed.

- Amber — at risk of slipping; actively being managed by the study team.

- Red — off track; requires escalation or a decision from sponsor / steering committee.

## Section C: Site Activation & Enrollment Status

Source these figures from the Site Activation Tracker (Component 4) and Recruitment Feasibility Template (Component 10).

| Metric | This Week | Cumulative | Target | % of Target |
| --- | --- | --- | --- | --- |
| Sites contracted |  |  |  |  |
| Sites with regulatory / EC approval |  |  |  |  |
| Sites activated (ready to enroll) |  |  |  |  |
| Subjects screened |  |  |  |  |
| Subjects screen-failed |  |  |  |  |
| Subjects enrolled / randomized |  |  |  |  |

Site-by-Site Detail

| Site ID / Name | Activation Status | Subjects Enrolled | Issues / Notes |
| --- | --- | --- | --- |

## Section D: Key Risks & Issues

Carry forward open items from the Risk Register (Component 7). Only new or materially changed items need commentary; do not duplicate the full register here.

| Risk / Issue | Impact | Owner | Mitigation / Next Action | Status |
| --- | --- | --- | --- | --- |

## Section E: Milestones & Upcoming Activities

Pull planned dates from the Start-Up Timeline (Component 6). Include the next 2–3 upcoming milestones plus any just completed.

| Milestone | Planned Date | Status | Notes |
| --- | --- | --- | --- |

## Section F: Action Items & Decisions Needed

Open items requiring someone's action, or a decision from the sponsor / steering committee, with a clear owner and due date.

| Action Item / Decision Needed | Owner | Due Date | Status |
| --- | --- | --- | --- |

Next report:  The next Weekly Status Report is due to the distribution list above on the same day next week. Any Red-rated work stream should be escalated immediately rather than held for the next scheduled report.