## About This Example
Site Activation Tracker — Completed Example
Filled-In Example Set — Toolkit Component 12 of 12
Case study
ORACLE-2 — the 8 sites selected for activation (Toolkit Component 3) as of 3 August 2026, roughly 6 weeks before the planned Week 0 activation date of 15 September 2026. SP-01 and SP-02 (the two top-ranked sites) are already activated, ahead of schedule. DE-02 shows the tracker's Delayed status in action — its contract was executed early, but downstream steps stalled amid the budget and staffing issues logged in the Risk Register (R-04, R-07).
Note on dates
Status is calculated live from TODAY() exactly as in the blank template. Values shown here are correct as of 3 August 2026; reopening this file on a later date will cause Days to Activation and Status to recalculate against the new current date, which is expected behavior, not an error.

## Activation Tracker
Site Activation Tracker — ORACLE-2
Completed example — snapshot as of 3 August 2026 (Week -6 of 12).
Target days to activation (contract → activation letter): |  |  |  | 49 | days (default: 7 weeks)
Site ID | Site Name | Country | Principal Investigator | Contract Executed | Essential Docs Complete | Regulatory / EC Approval | SIV Completed | IP Shipped | IP Received & Verified | EDC Access Granted | IRT Access Granted | Activation Letter Issued | Days to Activation | Status | Notes
SP-01 | Hospital Universitario del Sureste – Oncology Unit | Spain | Dr. Elena Ruiz Castellanos | 2026-06-22 | 2026-07-02 | 2026-07-08 | 2026-07-20 | 2026-07-24 | Yes | Yes | Yes | 2026-08-01 | 40 | Activated | Fastest site to activate; strong PI network
SP-02 | Barcelona Metropolitan Cancer Center | Spain | Dr. Marc Oliver Bosch | 2026-06-25 | 2026-07-04 | 2026-07-10 | 2026-07-22 | 2026-07-27 | Yes | Yes | Yes | 2026-08-01 | 37 | Activated | On track; activation letter issued 1 Aug 2026
SP-03 | Valencia Regional Oncology Institute | Spain | Dr. Laura Ibáñez Ferrer | 2026-06-29 | 2026-07-09 | 2026-07-15 | 2026-07-27 |  | No | Yes | No |  | 35 | In Progress | SIV completed; IP shipment and IRT access pending
PL-01 | Warsaw National Oncology Center | Poland | Dr. Anna Kowalska | 2026-06-30 | 2026-07-10 | 2026-07-20 |  |  | No | No | No |  | 34 | In Progress | Essential docs under final QC review
PL-02 | Kraków University Hospital – Oncology Dept. | Poland | Dr. Piotr Nowak | 2026-07-02 | 2026-07-14 |  |  |  | No | No | No |  | 32 | In Progress | EC approval pending; site coordinator following up weekly
PL-03 | Poznań Regional Cancer Institute | Poland | Dr. Katarzyna Zielińska | 2026-07-06 | 2026-07-16 | 2026-07-24 |  |  | No | No | No |  | 28 | In Progress | Activated despite Hold rating on Scorecard — enhanced monitoring plan applied (see Risk Register)
DE-01 | Berlin Metropolitan Oncology Research Unit | Germany | Dr. Thomas Weber | 2026-07-08 | 2026-07-18 |  |  |  | No | No | No |  | 26 | In Progress | EC approval submitted; on track for Week -4 SIV
DE-02 | Munich Central Oncology Institute | Germany | Dr. Julia Hoffmann | 2026-06-10 | 2026-06-25 | 2026-07-05 |  |  | No | No | No |  | 54 | Delayed | Delayed — competing trial and site staffing changes; see Risk R-04 (closed) and R-07
Formulas:
Days to Activation = IF([Contract Executed]="","",IF([Activation Letter Issued]="",TODAY()-[Contract Executed],[Activation Letter Issued]-[Contract Executed]))
Status = IF([Site ID]="","",IF([Contract Executed]="","Not Started",IF([Activation Letter Issued]<>"","Activated",IF((TODAY()-[Contract Executed])>E4,"Delayed","In Progress"))))

## Dashboard
Activation Dashboard
Live summary — updates automatically as you enter milestone dates.
Sites Tracked | 8
Sites Activated | 2
Sites In Progress | 5
Sites Delayed | 1
Sites Not Started | 0
Average Days to Activation (activated sites) | 38.5
Days to Activation by Site
Site Name | Days to Activation
Hospital Universitario del Sureste – Oncology Unit | 40
Barcelona Metropolitan Cancer Center | 37
Valencia Regional Oncology Institute | 35
Warsaw National Oncology Center | 34
Kraków University Hospital – Oncology Dept. | 32
Poznań Regional Cancer Institute | 28
Berlin Metropolitan Oncology Research Unit | 26
Munich Central Oncology Institute | 54