## About This Example
Essential Document Checklist — Completed Example
Filled-In Example Set — Toolkit Component 12 of 12
Case study
ORACLE-2 — this copy combines the Central / Sponsor documents with the site-specific documents for SP-01 (Hospital Universitario del Sureste), the fastest-activating site, as of 3 August 2026. Phase 1 (Before the Clinical Phase) is nearly complete, matching SP-01's activation status. Phase 2 items are mostly Not Started because enrollment has not opened yet (planned Week 0: 15 September 2026); Phase 3 is Not Started because the trial is not yet complete.

## Checklist
Essential Document Checklist — ORACLE-2 / SP-01
Completed example — Central + Site SP-01, snapshot as of 3 August 2026.
# | Document | ICH E6(R2) Ref. | Applies To | Status | Date Received | TMF Location | Notes
PHASE 1 — Before the Clinical Phase of the Trial Commences
1 | Investigator's Brochure (current version) | 8.2.1 | Central | Filed | 2026-06-20 | eTMF §2.1
2 | Signed protocol and protocol amendments | 8.2.2/8.2.3 | Central | Filed | 2026-06-22 | eTMF §1.1
3 | Sample case report form (blank) | 8.2.5 | Central | Filed | 2026-06-24 | eTMF §4.1
4 | Informed consent form template, including translations | 8.2.6 | Central | Filed | 2026-06-28 | eTMF §1.5 | ES/PL/DE translations
5 | Other written information provided to subjects | 8.2.7 | Central | Filed | 2026-06-28 | eTMF §1.6
6 | Advertisement for subject recruitment (if used) | 8.2.8 | Site-Specific | N/A |  |  | No active advertising — physician referral only
7 | Financial aspects of the trial (budget / payment schedule) | 8.2.9 | Site-Specific | Filed | 2026-07-05 | eTMF §3.1 (SP-01)
8 | Insurance statement / certificate | 8.2.10 | Central | Filed | 2026-07-08 | eTMF §2.4
9 | Signed Clinical Trial Agreement between parties | 8.2.11 | Site-Specific | Filed | 2026-07-08 | eTMF §3.2 (SP-01)
10 | IRB / EC approval of protocol, ICF, and related documents | 8.2.12 | Site-Specific | Filed | 2026-07-15 | eTMF §1.8 (SP-01)
11 | IRB / EC composition, or statement of GCP compliance | 8.2.13 | Site-Specific | Filed | 2026-07-15 | eTMF §1.9 (SP-01)
12 | Regulatory authority authorization / approval / notification | 8.2.14 | Central | Filed | 2026-07-18 | eTMF §1.3 | CTIS 2026-501234-10-00
13 | CVs and qualifications of investigator and sub-investigators | 8.2.15 | Site-Specific | Filed | 2026-07-10 | eTMF §3.3 (SP-01)
14 | Normal values / ranges for medical, laboratory, and technical procedures | 8.2.16 | Site-Specific | Filed | 2026-07-12 | eTMF §3.4 (SP-01)
15 | Laboratory certification, accreditation, or quality control procedures | 8.2.17/8.2.18 | Site-Specific | Received | 2026-07-28 |  | Awaiting final QC review
16 | Sample label(s) attached to investigational product containers | 8.2.19 | Central | Filed | 2026-06-30 | eTMF §2.6
17 | Instructions for handling investigational product and trial materials | 8.2.20 | Central | Filed | 2026-06-30 | eTMF §2.7
18 | Shipping records for investigational product and trial materials | 8.2.21 | Site-Specific | Requested |  |  | SP-03 / PL / DE shipments still in transit
PHASE 2 — During the Clinical Conduct of the Trial
1 | Updates to the Investigator's Brochure | 8.3.1 | Central | Not Started
2 | Any revised protocol, amendment, or ICF revision | 8.3.2 | Central | Not Started
3 | IRB / EC continuing review / re-approval | 8.3.3 | Site-Specific | Not Started |  |  | Applicable once enrollment opens
4 | CVs for any new investigators or sub-investigators | 8.3.4 | Site-Specific | Not Started
5 | Updated normal values / ranges, if changed during the trial | 8.3.5 | Site-Specific | Not Started
6 | Updated laboratory certification, if changed during the trial | 8.3.6 | Site-Specific | Not Started
7 | Documentation of investigational product accountability at the site | 8.3.7 | Site-Specific | Filed | 2026-07-30 | eTMF §5.1 (SP-01) | Accountability log initiated at IP receipt
8 | Signature sheet identifying roles and initials of study staff | 8.3.8 | Site-Specific | Filed | 2026-07-18 | eTMF §3.5 (SP-01)
9 | Monitoring visit reports | 8.3.9 | Site-Specific | Not Started |  |  | First monitoring visit scheduled post-FPI
10 | Relevant communications (letters, meeting notes, call notes) | 8.3.10 | Site-Specific | Not Started
11 | Signed informed consent forms | 8.3.11 | Site-Specific | Not Started |  |  | Applicable once enrollment opens
12 | Source documents | 8.3.12 | Site-Specific | Not Started
13 | Signed, dated, and completed case report forms (CRFs) | 8.3.13 | Site-Specific | Not Started
14 | Documentation of CRF corrections | 8.3.14 | Site-Specific | Not Started
15 | SAE / safety notifications between investigator and sponsor | 8.3.15/8.3.16 | Site-Specific | Not Started
16 | Interim or annual reports to IRB/EC and regulatory authority(ies) | 8.3.17/8.3.18 | Site-Specific | Not Started
17 | Subject screening and enrollment log | 8.3.19 | Site-Specific | Not Started |  |  | Distributed at SIV, blank until FPI
18 | Subject identification code list | 8.3.20 | Site-Specific | Not Started
PHASE 3 — After Completion or Termination of the Trial
1 | Final investigational product accountability and reconciliation | 8.4.1 | Site-Specific | Not Started
2 | Documentation of investigational product destruction | 8.4.2 | Site-Specific | Not Started
3 | Completed subject identification code list | 8.4.3 | Site-Specific | Not Started
4 | Audit certificate, if an audit was conducted | 8.4.4 | Central | Not Started
5 | Final trial close-out monitoring report | 8.4.5 | Site-Specific | Not Started
6 | Treatment allocation and decoding documentation | 8.4.6 | Central | Not Started
7 | Final report by investigator to IRB/EC and regulatory authority(ies) | 8.4.7 | Site-Specific | Not Started
8 | Clinical study report | 8.4.8 | Central | Not Started

## Dashboard
TMF Completion Dashboard
Live summary — updates automatically as you update the Status column.
Phase 1 Completion (Before Trial) | 88.24%
Phase 2 Completion (During Trial) | 11.11%
Phase 3 Completion (After Trial) | 0%
Overall TMF Completion | 39.53%
Documents Filed | 17
Documents Received (not yet filed) | 1
Documents Requested (awaited) | 1
Documents Not Started | 24
Documents N/A | 1
Completion by Phase
Phase | % Complete
Phase 1 — Before Trial | 88.24%
Phase 2 — During Trial | 11.11%
Phase 3 — After Trial | 0%