## About This Example
Start-Up Timeline — Completed Example
Filled-In Example Set — Toolkit Component 12 of 12
Case study
ORACLE-2 — Week 0 (planned site activation) is set to 15 September 2026. % Complete reflects real progress as of the 3 August 2026 snapshot (Week -6). Status is calculated live, exactly as in the blank template: it flags a phase once its Start Week has passed and % Complete is still below 100% — this is expected behavior of the tool, not an error, and is why several in-progress phases below show “Behind Schedule” even though they are legitimately still within their planned window.

## Timeline
Start-Up Timeline — ORACLE-2
Completed example — snapshot as of 3 August 2026 (Week -6).
Planned Week 0 date (site activation): |  |  |  | 2026-09-15
# | Phase / Milestone | Start Week | End Week | Owner | % Complete | Notes | W-12 | W-11 | W-10 | W-9 | W-8 | W-7 | W-6 | W-5 | W-4 | W-3 | W-2 | W-1 | W0 | W1 | W2 | Status
1 | Phase 1 — Protocol & Feasibility Finalization | -12 | -10 | Sponsor / Clin Ops | 100% | [16 empty] | Complete
2 | Phase 2 — Regulatory & Ethics Submissions | -10 | -6 | Regulatory Affairs | 90% | 1 open query with German BfArM; due Week -5 | [15 empty] | On Track
3 | Phase 3 — Site Identification & Selection | -12 | -8 | Feasibility Team | 100% | [16 empty] | Complete
4 | Phase 4 — Contracts & Budget | -10 | -6 | Legal / Contracts | 100% | Germany rate exception resolved — Risk R-04 | [15 empty] | Complete
5 | Phase 5 — Essential Document Collection (TMF) | -8 | -4 | CRA / TMF Lead | 78% | TMF ~78% filed — see Essential Document Checklist | [15 empty] | On Track
6 | Phase 6 — Site Activation | -6 | -2 | Project Manager | 25% | SP-01, SP-02 activated; DE-02 delayed — Risk R-04/R-07 | [15 empty] | On Track
7 | Phase 7 — Systems, Training & Communication | -8 | 0 | Project Manager | 60% | PV workflow end-to-end test scheduled Week -5 | [15 empty] | On Track
8 | Phase 8 — Recruitment Readiness | -4 | 0 | Recruitment Lead | 0% | Window opens Week -4 (18 Aug 2026) | [15 empty] | On Track
9 | Phase 9 — Final Readiness Review | 0 | 0 | Project Manager | 0% | Scheduled 15 Sept 2026 | [15 empty] | On Track
◆ | First Patient In (FPI) | 0 | 0 | CRA / Project Manager | 0% | Target: 15 September 2026
[7 empty] | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2
Formulas:
Status = IF(F5>=1,"Complete",IF(AND(TODAY()>(E3+[End Week]*7),F5<1),"Behind Schedule","On Track"))