## About This Example
Risk Register — Completed Example
Filled-In Example Set — Toolkit Component 12 of 12
Case study
ORACLE-2 — 9 risks logged and tracked between early June and 3 August 2026 (Week -6). Risk R-04 is the same risk referenced in the completed Study Start-Up Checklist as a Blocked item, and Risk R-06 is referenced in the completed Start-Up Timeline (Phase 2) as still in progress — this is what makes the toolkit's cross-references useful in practice: one register, cited consistently everywhere.

## Risk Register
Risk Register — ORACLE-2
Completed example — 9 risks logged as of 3 August 2026.
Risk ID | Risk Description | Category | Phase | Likeli- hood | Impact | Risk Score | Risk Level | Mitigation Plan | Owner | Status | Date Identified | Notes
R-01 | Central regulatory query response from Germany's competent authority delays CTIS approval beyond the planned 4-week window. | Regulatory | Phase 2 | 3 | 4 | 12 | High | Weekly follow-up call with the regulatory liaison; expedited query response prepared in advance. | Regulatory Affairs | Closed | 2026-06-25
R-02 | Candidate site Gdańsk University Hospital (Poland) scores below the activation threshold on Investigator & Team Experience — limited PI trial experience. | Site / Operational | Phase 3 | 3 | 2 | 6 | Medium | Site held as backup only; not selected for activation. Poland's enrollment allocation covered by PL-01–PL-03. | Feasibility Team | Closed | 2026-07-02 | See Site Selection Scorecard
R-03 | Insurance certificate delayed for Poland sites pending broker confirmation. | Financial / Budget | Phase 4 | 2 | 3 | 6 | Medium | Escalated to insurance broker; certificate obtained ahead of contract execution. | Legal / Contracts | Closed | 2026-07-10
R-04 | Germany site budget counter-proposal (DE-01, DE-02) exceeds the approved per-patient rate, threatening the contract execution timeline. | Financial / Budget | Phase 4 | 4 | 4 | 16 | Critical | Finance Director negotiated a revised rate within approved contingency (+8%); Sponsor approved the exception. | Finance / Project Manager | Closed | 2026-07-07 | Referenced as R-004 in Study Start-Up Checklist Phase 1
R-05 | PI GCP certificate expired at PL-03 (Poznań) ahead of the planned Site Initiation Visit. | Personnel / Resourcing | Phase 5 | 3 | 3 | 9 | Medium | Refresher GCP training scheduled and completed before the SIV. | CRA | Closed | 2026-08-01
R-06 | Investigational product shipment to Poland sites may be delayed at customs pending import license processing. | Vendor / Supply Chain | Phase 6 | 3 | 4 | 12 | High | Customs broker engaged 3 weeks ahead of planned shipment; import license application submitted early. | Regulatory Affairs / Pharmacy | In Progress | 2026-08-03 | See Start-Up Timeline, Phase 2 notes
R-07 | Central laboratory (contracted vendor) flags a capacity constraint for anticipated Q4 sample volume. | Vendor / Supply Chain | Phase 1 | 2 | 3 | 6 | Medium | Additional capacity reserved via contract amendment; confirmed in writing. | Vendor Management | Closed | 2026-07-15 | See Vendor Onboarding Checklist
R-08 | EDC build timeline compressed after a 1-week vendor resourcing delay. | Data / Systems | Phase 7 | 3 | 3 | 9 | Medium | Additional UAT resource added; build re-baselined with no impact to planned Week 0. | Data Management | Closed | 2026-07-20
R-09 | Munich Ethics Committee (DE-02) requests protocol clarification on inclusion criteria before granting approval. | Regulatory | Phase 2 | 3 | 2 | 6 | Medium | Clarification letter submitted; approval received without requiring a formal amendment. | Regulatory Affairs | Closed | 2026-08-10

## Risk Matrix
5×5 Risk Matrix — Live Heat Map
Each cell shows the number of logged risks at that Likelihood × Impact combination.
Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 1 | 0
3 | 0 | 2 | 2 | 2 | 0
2 | 0 | 0 | 2 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0
Low (1–4)
Medium (5–9)
High (10–15)
Critical (16–25)

## Dashboard
Risk Dashboard
Live summary — updates automatically as you log and score risks.
Total Risks Logged | 9
Critical | 1
High | 2
Medium | 6
Low | 0
Open / Escalated | 0
Mitigated / Closed | 8
Risks by Category
Category | Count
Regulatory | 2
Site / Operational | 1
Vendor / Supply Chain | 2
Financial / Budget | 2
Clinical / Safety | 0
Data / Systems | 1
Personnel / Resourcing | 1