## Instructions
RACI Matrix
Clinical Trial Start-Up Toolkit — Component 8 of 12
How this workbook works
This matrix assigns a Responsible, Accountable, Consulted, or Informed role to 9 functions across 22 key start-up activities, grouped by the same 9 phases used throughout the toolkit. A sensible default assignment is pre-filled based on common industry practice — edit any cell to match your organization's actual structure and delegation of authority.
The RACI definitions
R — Responsible: does the work to complete the activity.
A — Accountable: owns the outcome and signs off; exactly one A per activity, by definition.
C — Consulted: provides input before the activity is completed (two-way communication).
I — Informed: kept up to date after a decision or action (one-way communication).
Built-in validation
The Check column flags any row that does not have exactly one “A” — a common RACI error that creates either duplicate ownership or an accountability gap. A clean matrix shows “OK” in every row.
Distributing this matrix
Share the completed matrix with the full study team at kickoff (see the Study Start-Up Checklist, Component 1, Phase 7) and reference it explicitly in your Communication Plan and Weekly Status Report (Component 11) whenever ownership is unclear.
Color legend
Blue-filled cells are for your input (R/A/C/I letters). White cells contain formulas — do not overwrite them.
Educational and operational resource notice: this matrix is a professional starting framework based on common industry practice. It is not a substitute for your organization's own SOPs and does not constitute regulatory or legal advice. Adapt roles and assignments to your organization's actual structure and delegation of authority.

## RACI Matrix
RACI Matrix — Clinical Trial Start-Up
R = Responsible · A = Accountable (one per row) · C = Consulted · I = Informed
Phase | Activity # | Activity | Sponsor / Medical Director | Project Manager | Regulatory Affairs | Clinical Ops / CRA | Site / PI | Legal / Contracts | Data Management | Pharmacy / Vendor Mgmt | Quality Assurance | Check
Phase 1 | 1 | Finalize protocol synopsis and full protocol | A | R | C | I | I | I | C | I | I | OK
Phase 1 | 2 | Complete country and site feasibility assessment | I | A | C | R | C | I | I | I | I | OK
Phase 1 | 3 | Confirm CRO / vendor operating model and budget | A | R | I | C | I | C | I | C | I | OK
Phase 2 | 4 | Prepare and submit CTA / IND package | I | C | A | I | I | I | I | I | C | OK
Phase 2 | 5 | Submit to IRB / EC (central and local) | I | C | A | R | R | I | I | I | I | OK
Phase 2 | 6 | Obtain regulatory and IRB/EC approval | I | C | A | C | C | I | I | I | I | OK
Phase 3 | 7 | Score and rank candidate sites | I | A | I | R | I | I | I | I | I | OK
Phase 3 | 8 | Select and notify sites | C | A | I | R | C | I | I | I | I | OK
Phase 4 | 9 | Negotiate and execute Clinical Trial Agreement | I | C | I | I | C | A | I | I | I | OK
Phase 4 | 10 | Execute vendor contracts (lab, IRT, imaging) | I | C | I | I | I | A | C | R | I | OK
Phase 5 | 11 | Distribute and collect essential documents | I | C | I | A | R | I | I | I | I | OK
Phase 5 | 12 | QC review of TMF completeness | I | I | I | C | I | I | I | I | A | OK
Phase 6 | 13 | Conduct Site Initiation Visit (SIV) | I | C | I | A | R | I | C | I | I | OK
Phase 6 | 14 | Confirm IP shipment, receipt, and accountability | I | C | I | C | R | I | I | A | I | OK
Phase 6 | 15 | Issue site activation (“Green Light”) letter | I | A | C | R | I | I | I | I | C | OK
Phase 7 | 16 | Conduct investigator meeting | C | A | I | C | R | I | I | I | I | OK
Phase 7 | 17 | Set up CTMS and TMF structure | I | A | I | C | I | I | R | I | C | OK
Phase 7 | 18 | Confirm pharmacovigilance / SAE workflow | C | C | A | C | C | I | I | I | C | OK
Phase 8 | 19 | Finalize recruitment materials and IRB approval | I | A | C | R | C | I | I | I | I | OK
Phase 9 | 20 | Conduct final readiness review | C | A | C | C | C | I | I | I | C | OK
Phase 9 | 21 | Authorize site(s) for enrollment | A | R | I | I | I | I | I | I | I | OK
Phase 9 | 22 | Track and confirm First Patient In (FPI) | I | A | I | R | R | I | I | I | I | OK

## Dashboard
RACI Workload Dashboard
Live summary — counts how many activities each role is R / A / C / I on.
Role | R count | A count | C count | I count
Sponsor / Medical Director | 0 | 3 | 4 | 15
Project Manager | 3 | 9 | 9 | 1
Regulatory Affairs | 0 | 4 | 5 | 13
Clinical Ops / CRA | 7 | 2 | 8 | 5
Site / PI | 6 | 0 | 7 | 9
Legal / Contracts | 0 | 2 | 1 | 19
Data Management | 1 | 0 | 3 | 18
Pharmacy / Vendor Mgmt | 1 | 1 | 1 | 19
Quality Assurance | 0 | 1 | 5 | 16
Validation Summary
Activities with exactly 1 Accountable owner | 22
Activities needing a fix | 0
R + A Count by Role
Role | R+A Count
Sponsor / Medical Director | 3
Project Manager | 12
Regulatory Affairs | 4
Clinical Ops / CRA | 9
Site / PI | 6
Legal / Contracts | 2
Data Management | 1
Pharmacy / Vendor Mgmt | 2
Quality Assurance | 1