## About This Example
Vendor Onboarding Checklist — Completed Example
Filled-In Example Set — Toolkit Component 12 of 12
Case study
ORACLE-2 — the Onboarding Checklist sheet is completed for PanEuro Central Laboratories, the study's central lab vendor. The Multi-Vendor Tracker sheet shows all 8 vendors on the study as of 3 August 2026, including 2 still In Progress: Veridata Clinical Systems (EDC build finishing UAT) and RapidShip Logistics (Poland customs delay — see Risk R-06 in the Risk Register).

## Onboarding Checklist
Vendor Onboarding Checklist — PanEuro Central Laboratories
Completed example — ORACLE-2 central lab vendor, snapshot as of 3 August 2026.
Vendor Name | PanEuro Central Laboratories
Vendor Type | Central Lab
Contract Start Date | 08-Jul-2026
Onboarding Owner | Vendor Management
# | Checklist Item | Status | Date Completed | Notes
STAGE 1 — Selection & Due Diligence
1 | Vendor identified and added to preferred vendor list / RFP issued | Complete | 12-Jun-26
2 | References checked and prior performance reviewed | Complete | 15-Jun-26
3 | Financial stability and business continuity assessment completed | Complete | 17-Jun-26
4 | Quality system and certifications reviewed (e.g., ISO, GxP compliance) | Complete | 17-Jun-26 | ISO 15189 accredited
5 | Data privacy and security assessment completed (GDPR, 21 CFR Part 11 as applicable) | Complete | 18-Jun-26
6 | Capability assessment completed against protocol-specific requirements | Complete | 18-Jun-26
7 | Bid / quote received and reviewed against budget | Complete | 20-Jun-26
8 | Vendor selection approved by Sponsor / Procurement | Complete | 22-Jun-26
STAGE 2 — Contractual & Compliance Setup
1 | Confidentiality Disclosure Agreement executed | Complete | 24-Jun-26
2 | Master Service Agreement / vendor contract executed | Complete | 08-Jul-26
3 | Quality Agreement executed, where applicable | Complete | 08-Jul-26
4 | Data Processing Agreement / GDPR addendum executed | Complete | 08-Jul-26
5 | Insurance certificate obtained | Complete | 10-Jul-26
6 | Vendor added to sponsor's approved vendor list / procurement system | Complete | 10-Jul-26
7 | Purchase order / budget line raised | Complete | 11-Jul-26
8 | Vendor oversight plan drafted | Complete | 14-Jul-26
STAGE 3 — Operational & Systems Setup
1 | Kickoff meeting held with vendor project team | Complete | 15-Jul-26
2 | Roles, responsibilities, and communication plan agreed | Complete | 15-Jul-26
3 | Vendor-specific specifications finalized (e.g., lab manual, IRT spec, imaging charter) | Complete | 18-Jul-26 | Lab manual v1.0 approved
4 | System access provisioned for study team, if applicable | Complete | 20-Jul-26
5 | Integration with EDC / other systems tested, if applicable | Complete | 24-Jul-26 | Lab-to-EDC data feed tested
6 | Vendor staff trained on protocol and study-specific procedures | Complete | 24-Jul-26
7 | Escalation contacts and out-of-hours coverage confirmed | Complete | 25-Jul-26
8 | Vendor documentation filed in TMF | Complete | 28-Jul-26 | eTMF §2 — see Essential Document Checklist
STAGE 4 — Go-Live Readiness
1 | User acceptance testing (UAT) completed and signed off, if applicable | Complete | 29-Jul-26
2 | Vendor confirmed ready to support first site activation | Complete | 01-Aug-26
3 | Vendor KPIs and SLAs documented and agreed | Complete | 01-Aug-26 | 48-hour sample turnaround SLA
4 | First deliverable tested end-to-end (e.g., first shipment, first randomization) | In Progress |  | First sample kit shipment test scheduled Week -4
5 | Vendor oversight cadence scheduled (recurring calls, KPI reviews) | Complete | 01-Aug-26 | Monthly KPI review scheduled
6 | Final go-live sign-off obtained from Project Manager | Not Started |  | Pending first site activation
Overall % Complete: |  | 93.33%

## Multi-Vendor Tracker
Multi-Vendor Onboarding Tracker — ORACLE-2
Completed example — all 8 study vendors as of 3 August 2026.
Vendor Name | Vendor Type | Contract Executed | Kickoff Held | UAT / Systems Complete | Go-Live Ready | Owner | Onboarding Status | Notes
Meridian Clinical Solutions | CRO Functional Service | 20-Jun-26 | Yes | Yes | Yes | Vendor Mgmt | Ready | Full-service CRO, Spain & Poland
PanEuro Central Laboratories | Central Lab | 08-Jul-26 | Yes | Yes | No | Vendor Mgmt | In Progress | See Onboarding Checklist sheet — first shipment test pending
TrialLogic RTSM | IRT / RTSM | 08-Jul-26 | Yes | Yes | Yes | Vendor Mgmt | Ready | Stratified randomization 1:1 configured and tested
Veridata Clinical Systems | CRO Functional Service | 05-Jul-26 | Yes | No | No | Data Management | In Progress | EDC build in final UAT; go-live readiness Week -3
LinguaTrials Translations | Translation | 10-Jul-26 | Yes | Yes | Yes | Regulatory Affairs | Ready | ES/PL/DE ICF and materials translated and certified
RapidShip Logistics | Courier / Logistics | 12-Jul-26 | Yes | No | No | Regulatory Affairs / Pharmacy | In Progress | Poland customs / import license delay — see Risk R-06
CoreData eCOA Solutions | eCOA / ePRO | 15-Jul-26 | Yes | Yes | Yes | Data Management | Ready
PharmaSafe Pharmacovigilance Services | Safety / Pharmacovigilance | 14-Jul-26 | Yes | No | No | Pharmacovigilance | In Progress | End-to-end SAE workflow test scheduled Week -5

## Dashboard
Vendor Onboarding Dashboard
Live summary from the Multi-Vendor Tracker sheet.
Vendors Tracked | 8
Ready for Go-Live | 4
In Progress | 4
Not Started | 0
Vendors by Type
Type | Count
Central Lab | 1
IRT / RTSM | 1
Imaging | 0
Translation | 1
Courier / Logistics | 1
eCOA / ePRO | 1
Safety / Pharmacovigilance | 1
CRO Functional Service | 2
Other | 0