## About This Example
Recruitment Feasibility Template — Completed Example
Filled-In Example Set — Toolkit Component 12 of 12
Case study
ORACLE-2 — target enrollment 140 subjects across 8 sites, planned 10-month enrollment period. This example uses a later snapshot than the other completed documents in this set: 30 January 2027, roughly 4.5 months after First Patient In (15 September 2026), so the Enrollment Projection Tracker has real actuals to show. Site DE-02 (Munich) is rated At Risk after a competing trial opened at the site in September 2026 — logged as Risk R-07 in the Weekly Status Report for this period.

## Site Feasibility Calculator
Site Feasibility Calculator — ORACLE-2
Completed example — 8 activated sites plus 1 backup, snapshot as of 30 January 2027.
Study-Wide Target Enrollment (subjects) |  |  |  | 140
Planned Enrollment Period (months) |  |  |  | 10
Number of Sites Planned |  |  |  | 8
# | Site ID / Name | Country | Site Target Enrollment | Eligible Patient Pool (est.) | Historical Screen Failure Rate | Est. Monthly Screening Rate | Competing Trials at Site | Est. Monthly Enrollment Rate | Months to Site Target | Feasibility Rating | Notes
1 | SP-01 — Hospital Universitario del Sureste | Spain | 22 | 190 | 30% | 15 | 1 | 10.5 | 2.1 | Feasible
2 | SP-02 — Barcelona Metropolitan Cancer Center | Spain | 20 | 160 | 35% | 12 | 1 | 7.8 | 2.6 | Feasible
3 | SP-03 — Valencia Regional Oncology Institute | Spain | 18 | 140 | 38% | 10 | 1 | 6.2 | 2.9 | Feasible
4 | PL-01 — Warsaw National Oncology Center | Poland | 18 | 150 | 30% | 11 | 1 | 7.7 | 2.3 | Feasible
5 | PL-02 — Kraków University Hospital | Poland | 16 | 120 | 33% | 9 | 1 | 6 | 2.7 | Feasible
6 | PL-03 — Poznań Regional Cancer Institute | Poland | 16 | 110 | 36% | 8 | 2 | 5.1 | 3.1 | Feasible | Enhanced monitoring plan in place (Hold-rated site)
7 | DE-01 — Berlin Metropolitan Oncology Research Unit | Germany | 16 | 130 | 40% | 7 | 1 | 4.2 | 3.8 | Feasible
8 | DE-02 — Munich Central Oncology Institute | Germany | 14 | 100 | 42% | 2 | 3 | 1.2 | 11.7 | At Risk | Competing trial NCT-EXT-3391 opened Sep 2026 — Risk R-07
9 | PL-04 — Gdańsk University Hospital (backup) | Poland |  | 100 | 45% | 4 | 2 |  |  |  | Backup — not activated; held in reserve for Poland
10
11
12
Sum of Site Targets: |  |  | 140
Variance vs. Study-Wide Target: |  |  | 0

## Competing Studies Log
Competing Studies Log — ORACLE-2
Completed example — competing trials logged as of 30 January 2027.
# | Site ID / Name | Competing Protocol / Study ID | Sponsor | Indication | Same Target Population? | Estimated Impact on Enrollment | Status | Notes
1 | DE-02 — Munich Central Oncology Institute | NCT-EXT-3391 | Northgate Bio-Pharma AG | 2nd-line advanced NSCLC (same population) | Yes | High | Recruiting | Opened Sep 2026; same referring pulmonology network as DE-02 — Risk R-07
2 | SP-02 — Barcelona Metropolitan Cancer Center | NCT-EU-2287 | Iberia Oncology Research | 1st-line NSCLC (different line of therapy) | No | Low | Recruiting | Low overlap; different treatment line
3 | PL-01 — Warsaw National Oncology Center | EUCT-2026-441 | Baltic Clinical Research | Mixed solid tumor basket trial | No | Low | Recruiting | Minimal eligible-population overlap
4
5
6
7
8
9
10
11
12
13
14
15

## Enrollment Projection Tracker
Enrollment Projection Tracker — ORACLE-2
Completed example — Month 1 = October 2026 (post FPI 15 Sep 2026); snapshot as of Month 4 (30 Jan 2027).
# | Month | Planned Cumulative Enrollment | Actual Cumulative Enrollment | Variance | Notes
1 | Month 1 | 14 | 10 | -4 | All 8 sites activated and enrolling by end of September 2026
2 | Month 2 | 28 | 24 | -4 | Screening pace below plan at DE-02 — competing trial opened (Risk R-07, 20 Sep 2026)
3 | Month 3 | 42 | 39 | -3 | Backup recruitment support engaged at DE-02; Spain and Poland sites over-performing plan
4 | Month 4 | 56 | 55 | -1 | Enrollment gap narrowed to -1 subject; overall trajectory tracking to the Month 10 target
5 | Month 5 | 70
6 | Month 6 | 84
7 | Month 7 | 98
8 | Month 8 | 112
9 | Month 9 | 126
10 | Month 10 | 140
11 | Month 11 | 140
12 | Month 12 | 140
13 | Month 13 | 140
14 | Month 14 | 140
15 | Month 15 | 140
16 | Month 16 | 140
17 | Month 17 | 140
18 | Month 18 | 140

## Dashboard
Recruitment Feasibility Dashboard
Live summary — ORACLE-2, snapshot as of 30 January 2027.
Study-Wide Target Enrollment | 140
Planned Enrollment Period (months) | 10
Sites Rated Feasible | 7
Sites Rated At Risk | 1
Sites Rated Not Feasible | 0
Current Actual Enrollment | 55
% of Target Achieved | 39.29%
Site Feasibility Distribution
Rating | Sites
Feasible | 7
At Risk | 1
Not Feasible | 0