CLINICAL TRIAL START-UP TOOLKIT — FILLED-IN EXAMPLE SET Weekly Status Report — Completed Example: Week of 26–30 January 2027 — Component 12 of 12 — Worked Example: Protocol ORACLE-2, 4.5 months into enrollment Sample Document — Prepared for Internal Review Fictional case study — all names, sites, and data are illustrative, not real Version 1.0 — 3 August 2026 expertclinicaltrials.com

# About This Worked Example

This is the Weekly Status Report (Toolkit Component 11) completed for the reporting period 26–30 January 2027 — roughly Month 4 of ORACLE-2's planned 10-month enrollment period, and about 4.5 months after First Patient In (15 September 2026). It uses a later date than the other 10 completed documents in this example set, deliberately, so the enrollment and risk sections have real progress to show. See the completed Recruitment Feasibility Template for the same snapshot.

# Weekly Status Report

| Question | Response |
| --- | --- |
| Protocol number / Study title | ORACLE-2 — Phase II Study of [Investigational Agent] vs. SoC in 2nd-Line Advanced NSCLC |
| Sponsor / CRO | Solara Oncology Therapeutics, S.A. / Meridian Clinical Solutions (full-service, ES/PL) |
| Reporting period (week of) | 26–30 January 2027 |
| Report prepared by (name, role) | Carlos Fernández Mora, Project Manager |
| Distribution list | Sponsor Clinical Operations, Regulatory Affairs, Biostatistics, Data Management, CRA Team |
| Overall Project Status | Amber — driven by recruitment; all other work streams Green |

## Section A: Executive Summary

- 55 of 140 subjects enrolled (39%) at Month 4 of the planned 10-month enrollment period; trajectory improving after a slow start — the gap vs. plan narrowed to -1 subject this month.

- All 8 sites activated and enrolling; no new site activations planned this period.

- DE-02 (Munich) remains the primary recruitment risk after a competing trial (NCT-EXT-3391) opened in the same indication in September 2026 — logged as Risk R-07. A backup German site is under evaluation; decision due 15 February 2027.

- No new regulatory, contract, or vendor issues this reporting period.

## Section B: RAG Status by Work Stream

| Work Stream | Last Week | This Week | Trend | Comments |
| --- | --- | --- | --- | --- |
| Regulatory & Ethics Approvals | Green | Green | → | No open queries |
| Contracts & Budget | Green | Green | → | No change |
| Site Activation | Green | Green | → | All 8 sites active since Sep 2026 |
| Recruitment & Enrollment | Amber | Amber | ↗ | Gap narrowing; DE-02 remains at risk (R-07) |
| Vendors & Third Parties | Green | Green | → | All 8 vendors Ready |
| IP / Supply Chain | Green | Green | → | Poland customs delay (R-06) resolved Aug 2026 |
| Systems & Data (EDC / IRT) | Green | Green | → | No open issues |

RAG definitions:

- Green — on track against plan; no action needed.

- Amber — at risk of slipping; actively being managed by the study team.

- Red — off track; requires escalation or a decision from sponsor / steering committee.

## Section C: Site Activation & Enrollment Status

| Metric | This Week | Cumulative | Target | % of Target |
| --- | --- | --- | --- | --- |
| Sites contracted | 0 | 8 | 8 | 100% |
| Sites with regulatory / EC approval | 0 | 8 | 8 | 100% |
| Sites activated (ready to enroll) | 0 | 8 | 8 | 100% |
| Subjects screened | 6 | 89 | — | — |
| Subjects screen-failed | 2 | 34 | — | — |
| Subjects enrolled / randomized | 4 | 55 | 140 | 39% |

Site-by-Site Detail

| Site ID / Name | Activation Status | Subjects Enrolled | Issues / Notes |
| --- | --- | --- | --- |
| SP-01 — Hospital Universitario del Sureste | Active | 12 |  |
| SP-02 — Barcelona Metropolitan Cancer Center | Active | 10 |  |
| SP-03 — Valencia Regional Oncology Institute | Active | 8 |  |
| PL-01 — Warsaw National Oncology Center | Active | 9 |  |
| PL-02 — Kraków University Hospital | Active | 7 |  |
| PL-03 — Poznań Regional Cancer Institute | Active | 6 | Enhanced monitoring per Scorecard Hold rating; on track |
| DE-01 — Berlin Metropolitan Oncology Research Unit | Active | 2 | Slower start; within normal range for site size |
| DE-02 — Munich Central Oncology Institute | Active | 1 | At Risk — competing trial impacting screening (R-07) |

## Section D: Key Risks & Issues

| Risk / Issue | Impact | Owner | Mitigation / Next Action | Status |
| --- | --- | --- | --- | --- |
| R-07 — Competing trial (NCT-EXT-3391, same indication) at DE-02 (Munich) reducing the eligible patient pool. | High | Recruitment Lead | Monitor competing-trial enrollment monthly via the Competing Studies Log; evaluate a backup German site if the gap persists beyond Month 5. | Open |
| R-06 — Investigational product shipment delay at Poland customs. | Medium | Regulatory Affairs / Pharmacy | Resolved — customs broker engagement cleared all pending shipments. | Closed |
| R-04 — Germany site budget counter-proposal (DE-01, DE-02). | High | Finance / PM | Resolved — revised rate agreed within approved contingency. | Closed |

## Section E: Milestones & Upcoming Activities

| Milestone | Planned Date | Status | Notes |
| --- | --- | --- | --- |
| First DSMB Safety Review | 15-Feb-2027 | On Track | Data cut 31 Jan 2027 |
| Backup German site activation decision | 15-Feb-2027 | Pending | Contingent on DE-02 trend through Month 5 |
| 50% Enrollment Milestone (70 subjects) | ~Mar-2027 | On Track | Projected at current pace |
| Interim database lock (50% enrollment) | Apr-2027 | Not Started |  |

## Section F: Action Items & Decisions Needed

| Action Item / Decision Needed | Owner | Due Date | Status |
| --- | --- | --- | --- |
| Decide on backup German site activation | Recruitment Lead / Sponsor | 15-Feb-2027 | Pending |
| Finalize DSMB briefing package | Medical Monitor | 10-Feb-2027 | In Progress |
| Confirm Q1 investigational product supply forecast with PanEuro / TrialLogic | Vendor Management | 07-Feb-2027 | Not Started |

Next report:  The next Weekly Status Report is due to the distribution list above on Friday, 6 February 2027. The backup German site decision (Action Item, Section F) should be escalated immediately if not resolved by 15 February, rather than held for the next scheduled report.